T-structure turning construction technology Frame

Foundation 1st fioor

concrering

Welding foundation steel,preserved

piersted of pier

Installing sub-table sted

plate&stedaxle axle

Foundation top concreting

&supporting colunn

Sub-circle way sand

Mortar leveling

Sub-table sted plate painting

Grease fluorine powder

Hoisting upper table sted

plate to proper place

Erecting form & concreting upper table&temporary support

Concreting pier

Erecting form & concreting beam

Section No.0.1.1’

Reaching design

Upper table insert fluorine mushroom end ,painting grease

requirement

Removing Supports

concrete strength reaching

Tensioning beam Section No.0,1&1’

Concreting symmtrey beam section from2（2ˊ）to10（10ˊ）,lapping supports to concrete from 12（12ˊ）to15（15ˊ）

over 85%than design value

Removing temporary Support on turntable

Temporary strand

tension

Connection section

concreting

Turning body

Sealing Table

Welding connection section 11（11ˊ）skeleton

concrete strength reaching

Bottom Plate Vertical Prestress tension

Concreting & sealing

Removing

Temporary strand

Connection

Section tension

Removing supports of

Cast-in-place section

Erecting border span

T-beam

Bridge pavement

over 85%than design value